## Journal de travail
work diary
Alex Kamano |  |  |  |  | Tasks
Date | Time | Start time | End time | others | Description
2026-02-02 | 3:10 | 13:20 | 16:30 | Documentation | Create the planification, IceScrum and the repot Git
2026-02-03 | 0:40 | 9:05 | 9:45 | Analysis/Design | Create the MLD + Mcd for the DB
2026-02-03 | 0:34 | 9:45 | 10:19 | Analysis/Design | Create the database
2026-02-03 | 0:08 | 10:19 | 10:27 | Documentation | Update the IceScrum by addinf task on the story 1
2026-02-03 | 0:23 | 10:27 | 10:50 | Analysis/Design | Start creating the wireframe for the UI/UX
2026-02-03 | 0:30 | 13:20 | 13:50 | Analysis/Design | Finish to create the wireframe for the UI/UX
2026-02-03 | 0:10 | 13:50 | 14:00 | Documentation | Update the IceScrum by adding task on the story 3
2026-02-03 | 0:40 | 14:00 | 14:40 | Analysis/Design | Create the skeleton of the project. Utilisation de Gemini pour générer un .gitignore standardisé pour Python afin d'éviter de polluer le repo Git
2026-02-03 | 0:50 | 14:40 | 15:30 | Analysis/Design | Architecture du projet
2026-02-03 | 0:10 | 15:30 | 15:40 | Documentation | Update the IceScrum by addinf task on the story 1
2026-02-03 | 0:26 | 15:40 | 16:06 | Analysis/Design | Brainstorming about the routes and planification on how to organise it
2026-02-03 | 0:29 | 16:06 | 16:35 | Documentation | Put all the actuals documentation on github and push the skeleton of the project
2026-02-04 | 0:45 | 15:05 | 15:50 | Meeting | Meeting with the project's chief to discuss about the CDC
2026-02-04 | 0:50 | 15:50 | 16:40 | Documentation | Update of the data and publish it on Github
2026-02-09 | 1:37 | 13:20 | 14:57 | Implementation | Add the logic to login and register
2026-02-09 | 1:35 | 15:05 | 16:40 | Implementation | Add some security about the coockies, sessions and pwd
2026-02-10 | 0:57 | 8:00 | 8:57 | Documentation | Update the IceScrum for the story 4
2026-02-10 | 0:23 | 8:57 | 9:20 | Implementation | Add the function logout
2026-02-10 | 0:55 | 9:20 | 10:15 | Documentation | Add some comentary
2026-02-10 | 0:45 | 13:20 | 14:05 | Documentation | Write of the final report
2026-02-10 | 1:40 | 14:20 | 16:00 | Implementation | Add the page register, login, home and base with the css
2026-02-10 | 0:40 | 16:00 | 16:40 | Documentation | Write of the final report
2026-02-11 | 1:35 | 15:05 | 16:40 | Documentation | Write of the final report
2026-02-23 | 0:18 | 10:37 | 10:55 | Meeting | Discussion with the PO about the correction to make on the project
2026-02-23 | 1:35 | 13:20 | 14:55 | Analysis/Design | Rewrite the MCD/MLD due to some bug about the functionnalities
2026-02-23 | 1:35 | 15:05 | 16:40 | Documentation | Add a wiki to the repo and add the current documentation too
2026-02-24 | 1:35 | 15:05 | 16:40 | Documentation | Start to create the project GIT
2026-03-03 | 3:30 | 9:00 | 12:30 | Implementation | Start creating paygame
2026-03-03 | 0:40 | 13:20 | 14:00 | Implementation | Finsih the base of the game
2026-03-03 | 2:40 | 14:00 | 16:40 | Documentation | Continue to create the project GIT
2026-03-04 |  | 15:45 |  | Documentation | Update the report

## Planification
Project MA-Métier - Initial Plan
Project start: | 2026-02-02 | 2026-03-04 |  | février | [19 empty] | mars | [21 empty] | avril
| 0 |  |  | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-29 | 1900-01-30 | 1900-04-01 | 1900-04-02 | 1900-04-03
Description | Category | Start date | Days
Create the initial planing | Analysis/Design | 2026-02-02 | 1
MCD + MLD + DB | Analysis/Design | 2026-02-03 | 2
Project skeleton setup | Analysis/Design | 2026-02-09 | 1
UI/UX wireframes | Analysis/Design | 2026-02-10 | 2
Api endpoints setup | Implementation | 2026-02-16 | 2
User Auth System | Implementation | 2026-02-16 | 2
Game core pygame | Implementation | 2026-02-18 | 4
Game api integration | Implementation | 2026-03-02 | 2
swagger doc api | Analysis/Design | 2026-03-03 | 1
web leaderboard view | Implementation | 2026-03-04 | 4
securtiy data validation | Analysis/Design | 2026-03-16 | 2
user install manuals | Documentation | 2026-03-17 | 2
write the documentation in continue | Documentation | 2026-02-09 | 21
Prepera the oral | Analysis/Design | 2026-03-25 | 4
Low Risk
Project MA-Métier - Current Plan
Project start: | 2026-02-02 | 2026-03-04 |  | février | [19 empty] | mars | [21 empty] | avril
0 | 0 |  |  | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-29 | 1900-01-30 | 1900-04-01 | 1900-04-02 | 1900-04-03
Description | Category | Start date | Days
Create the initial planing | Analysis/Design | 2026-02-02 | 2
MCD + MLD + DB | Analysis/Design | 2026-02-03 | 1
Project skeleton setup | Analysis/Design | 2026-02-09 | 1
UI/UX wireframes | Analysis/Design | 2026-02-10 | 1
Api endpoints setup | Implementation | 2026-02-16 | 1
User Auth System | Implementation | 2026-02-16 | 2
Game core pygame | Implementation | 2026-02-18 | 1
Game api integration | Implementation | 2026-03-02
swagger doc api | Analysis/Design | 2026-03-03
web leaderboard view | Implementation | 2026-03-04
securtiy data validation | Analysis/Design | 2026-03-16
user install manuals | Documentation | 2026-03-17
write the documentation in continue | Documentation | 2026-02-09 | 11
Prepera the oral | Analysis/Design | 2026-03-25
Formulas:
Start date = IFERROR(IF(MIN(Milestones4354[Days])=0,TODAY(),#REF!(Milestones4354[Days])),TODAY())